DRC Cross-Network Payment App

MVP Build Plan & Cost Estimate

Investor & Stakeholder Summary

16-week build to code freeze  -  Figures in US dollars

Important - please read These are estimations for contracted work. The exact costs and deadlines are subject to change depending on development progress. Technical details are also subject to change depending on the feasibility of solutions and the preferences of the developers as new team members are brought on.

# Cost summary

How these costs are calculated:

- Rate: $80 per hour, per contractor (contracted work). New team member rates may differ from this $80/hr figure.

- Retainer: 20% of total expenditure

- Team: 2 contractors in Weeks 1-2; 4 contractors from Week 3 onward, as new team members are brought on.

- Effort: each contractor works 10-20 hours per week.

- Scope: this document covers contractor labor only.

| Phase | Weeks | Team | Weekly cost | Phase total |
| --- | --- | --- | --- | --- |
| Ramp-up | 1-2 | 2 | $1,600 - $3,200 | $3,200 - $6,400 |
| Full build | 3-16 | 4 | $3,200 - $4,800 | $44,800 - $67,200 |
| Projected 16-week build total |  |  |  | $48,000 - $73,600 |

Budget Goal for MVP: $40,000

Retainer: $8,000

## Beyond this phase

This plan ends at code freeze: a finished, tested app ready to launch. Taking it live to the public is a separate, following phase.

- Next phase - going live (about 4-8 weeks, team of 4): Covers switching to real money, a small closed test with friends and family, and publishing to the app stores.

Marketing, ongoing running costs after launch, and any non-labor costs (such as legal counsel, cloud hosting, app-store accounts, and test phones) are not included in these figures.

# Deliverables

Across 16 weeks the project produces six concrete outcomes:

- A working money-transfer app. A polished phone app (iPhone and Android) where a user signs up with their phone number and sends money in a few taps.

- Cross-network payments proven. The core promise: send from one mobile money network to any other - something users cannot easily do today.

- No Internet Functionality (USSD) – allow for cross-network payments when internet is not available on the consumer’s phone.

- Trustworthy and safe. See the recipient's name before paying, automatic refunds when a payment fails, and a precise internal record of every transaction.

- Built for DRC. Multiple language options, works on low-cost Android phones and shaky networks, and designed around how Congolese actually pay and share proof.

- Ready to launch on demand. Fully tested, documented, and frozen, so the business can flip the switch to 'live' whenever conditions are right.

# Timeline Summary

The expenditures are projected averages of part-time work for the summer and to retain the services of team members. Actual weekly hours may vary from member-to-member and week-to-week. The estimated costs may be lower than estimated if certain team members are not needed for certain tasks. Estimated costs will generally not exceed max weekly amount unless unforeseen circumstances present themselves.

Two stages. Foundation stage: sets up the team, designs, and accounts, resolves the legal question, and proves a first test payment. Build stage: turns model into a full, tested product. Some milestones to mark the path; a working cross-network, USSD functionality payment, QR code generation and functionality and code freeze (end of MVP).

Weekly Cost and Potential Work:

| Wk | Focus | Team | Est. cost |
| --- | --- | --- | --- |
| 1 | Kickoff, Research, Formulation | 2 | $1,600 – $3,200 |
| 2 | Architecture locked & accounts opened | 2 | $1,600 – $3,200 |
| 3 | Designs done & app shell navigable | 4 | $3,200 - $4,800 |
| 4 | Sign-up works & first test payment | 4 | $3,200 - $4,800 |
| 5 | The money-records backbone | 4 | $3,200 - $4,800 |
| 6 | Sending money: taking the payment, delivering payment | 4 | $3,200 - $4,800 |
| 7 | USSD Functionality | 4 | $3,200 - $4,800 |
| 8 | USSD UI Development | 4 | $3,200 - $4,800 |
| 9 | USSD Integration with Main App | 4 | $3,200 - $4,800 |
| 10 | Full cross-network payment, end-to-end (milestone) | 4 | $3,200 - $4,800 |
| 11 | History & receipts | 4 | $3,200 - $4,800 |
| 12 | Handling the edge cases/Support Tools | 4 | $3,200 - $4,800 |
| 13 | Everything in proper relevant languages | 4 | $3,200 - $4,800 |
| 14 | Speed & reliability under pressure | 4 | $3,200 - $4,800 |
| 15 | Team use & bug bash | 4 | $3,200 - $4,800 |
| 16 | Code freeze - MVP complete (milestone) | 4 | $3,200 - $4,800 |

# Things that could affect the timeline

A few things outside the building work are depended upon. Most are quick; one - the legal question - is the real watch item, which is why it is started in Week 1.

- Legal opinion (high importance): whether we can operate on the payment partner's license or need our own. Started Week 1, needed by Week 4. If the answer requires our own license, that is a much larger, separate undertaking - so it is resolved first.

- Payment-partner test access: a free, instant, self-serve account. Low risk.

- Payment-partner live-money approval: needed only for the next phase (going live), not this build. Started early so the clock is running.

- App-store accounts and test phones/SIM cards: simple, low-cost, low-risk setup in the first few weeks.